## Issues
# | Bot | Severity | ACTIVE/LATENT | Symptom | D-pattern | Status
1 | kkb-hi-in (+kn twin) | HIGH | ACTIVE | New inbound caller: apply_job sent a fabricated/empty profile_id with no create_profile -> 404 (new callers can't apply) | D31/D16/D28 | FIXED+deployed (verify-pending: inbound) - repro 5449910e,34f1f587
2 | kkb-hi-in (+kn twin) | MED | ACTIVE | hold_message narrates the 'silent' get_profile/create_profile aloud | D34 | FIXED+deployed (verify-pending: inbound) - repro 8ddcaa5a,1fde1677
3 | kkb-hi-in | HIGH | LATENT | Memory-resume opener may speak name/role/journey before/instead of get_profile | D32 | deferred->open-items#6 (probe 8ddcaa5a: fetch still fired)
4 | kkb-hi-in | LOW | LATENT | Canonical-location list pins only 5 places vs a much larger Job Inventory | D26 | latent
5 | kkb-hi-in | LOW | LATENT | +91 hard-prepend template (landmine); inbound contact_phone is bare-10-digit so it doesn't fire | D17/C3 | deferred->open-items#3
6 | kkb-hi-out (+kn twin) | MED | LATENT->ACTIVE | hold_message narrates the silent fetch/create | D34 | FIXED+VERIFIED live on kkb-kn-out (neutral 'ಒಂದು ನಿಮಿಷ' hold in 7e5e1173/ab930586)
7 | kkb-hi-out | HIGH | LATENT/no-repro | +91 hard-prepend on get_profile/create_profile -> +91+91... if dialer sends prefixed phone | D17/C3 | deferred->open-items#3
8 | kkb-hi-out | MED | LATENT | Memory-resume 'Strict Override' + Example 2 model skipping get_profile -> apply w/o profile_id | D32/E1 | deferred->open-items#6
9 | kkb-hi-out | MED | LATENT | Outbound bot invites callbacks in closings ('call कीजिए') | D5 | latent
10 | kkb-hi-out | LOW | LATENT | Apply-failure turn lacks the 'don't re-speak the bridge' guard (D27 parity) | D27 | latent
11 | kkb-kn-out | MED | ACTIVE->VERIFIED | hold_message spoken; 'info received' said even on an EMPTY fetch [] | D34 | FIXED+VERIFIED live (neutral hold in 7e5e1173/ab930586)
12 | kkb-kn-out | HIGH | INTERMITTENT | create_profile/get_profile phone occasionally mangled to '+9197946350285' -> HTTP 400 | D17/D39 | INTERMITTENT - clean in 7e5e1173, mangled in ab930586; test used non-prod +91 format; open-items#2/#3 (deterministic last-10+one-+91 rule ready)
13 | kkb-kn-out | HIGH | LATENT | Memory-resume opener may substitute for get_profile | D32 | deferred->open-items#6 (probe fa530906: fetch fired, no resume)
14 | kkb-kn-out | MED | LATENT | +91 double-prefix landmine | D17/C3 | deferred->open-items#3
15 | kkb-kn-out | MED | LATENT | Ranking pads to 3 with unrelated roles (no relevance filter) | D36 | latent
16 | kkb-kn-out | MED | LATENT | Apply-failure D27 guard(a) missing; same-job re-fire guard scoped to alt path only | D27 | latent
17 | kkb-hi-signals (+kn twin) | HIGH | ACTIVE->RESOLVED | New-seeker create_profile without location -> profile draft -> apply_job 422 PROFILE_NOT_LIVE | D40 | RESOLVED (tool-schema location required, 2026-07-29) - repro fb1283cb; verify schema stuck
18 | kkb-hi-signals | HIGH | LATENT | create/update_profile phone spec: 10-digit vs 12-digit self-contradiction -> wrong-user write | D39/C3/A4 | latent (prose hygiene)
19 | kkb-hi-signals | MED | LATENT | Phase-2 examples contradict rules (working/studying asked, vague count, non-schema totalYearsOfExperience) | E1/C3 | latent
20 | kkb-hi-signals | MED | LATENT | New-caller create-consent line speaks 'प्रोफाइल' aloud | D8 | latent
21 | kkb-hi-signals | MED | LATENT | get_profile 91-prepend double-prefix landmine | D17 | latent
22 | kkb-hi-signals | LOW | LATENT | Example 6 malformed (two closings) + duplicate No-Match sections | E1 | latent
23 | kkb-kn-signals | MED | ACTIVE->RESOLVED | apply_job on a draft items[0] while a live item existed -> 422 PROFILE_NOT_LIVE | D37/D40 | RESOLVED (live-item selection, 2026-07-29) - eaa3f2d1 failed pre-fix; 5804fd6b/b3ef7abe pass
24 | kkb-kn-signals | MED | LATENT | create_profile phone 10-vs-12-digit contradiction (twin of #18) | D39/C3/A4 | latent (prose hygiene)
25 | kkb-kn-signals | MED | LATENT | Outbound bot invites callbacks in closings | D5 | latent
26 | kkb-kn-signals | LOW | verify | D40 location-required is only durable at the tool-schema level; not verifiable in the prompt | D40 | verify-pending (agent config)
27 | kkb-hi-signals (+kn twin) | MED | ACTIVE (feature gap) | Returning caller wants a different role - bot switched job/applied but never offered to update the stored role; multi-profile not treated 1:1 | feature | FIXED+deployed (role-update offer + 1:1 principle, 2026-07-29) - found a0c24a1d, verified 15e3f9d9
28 | maya-hi | HIGH | LATENT/no-repro | get_profile +91 hard-prepend (line 273) -> double-prefix on returning caller | D17/C3 | deferred->open-items#3
29 | maya-hi | MED | LATENT | hold_message narrates the silent fetch | D34 | latent
30 | maya-hi | MED | LATENT | Memory-resume intro competes with get_profile (memory-as-fetch) | D32 | deferred->open-items#6
31 | maya-hi | MED | LATENT | 'Present 3 best-fit' ranks but never filters -> pads unrelated roles | D36 | latent
32 | maya-hi | LOW | LATENT | Rare create->apply fallback (+ out/in batching language) lacks a tool-result boundary | D31 | deferred->open-items#9 (Maya out is harness-testable)
33 | dkb-hi (+kn twin) | MED | ACTIVE | Silent tools (create_job/update_job_*) hold_message narrated aloud | D34 | FIXED+deployed (verify-pending: DKB Kn call) - repro cf3fc048
34 | dkb-hi (+kn twin) | MED | ACTIVE | Outbound close invites a callback ('ज़रूर फोन करना' / 'ಖಂಡಿತ phone ಮಾಡಿ') | D5 | FIXED+deployed (verify-pending: DKB Kn call) - repro cf3fc048
35 | dkb-hi | MED | LATENT | update_job_details lacks the English/Latin-payload rule -> Devanagari can leak into the payload | D3/C4 | latent
36 | dkb-hi | MED | LATENT | ${phoneNumber} undeclared + inconsistent phone format across the 3 payloads | C3/C2 | deferred->open-items#4
37 | dkb-hi | LOW | LATENT | Female persona has no feminine-verb rule; line 99 uses masculine 'समझ गया' | D4 | latent
38 | dkb-hi | LOW | LATENT | No voicemail/IVR bounded exit; no off-topic / are-you-AI / do-not-call handlers | E4 | latent
39 | dkb-kn | MED | ACTIVE-non-breaking | create_job phoneNumber:'Not Available' (var unbound) + bare-10-digit example vs Hindi's +91 | C3/C2 | deferred->open-items#4
40 | dkb-kn | LOW | LATENT | Graceful-Exit sync drift: Kannada omits Hindi's confirm/reflect pre-close step | F | latent
41 | dkb (campaign) | - | ACTIVE (data) | Scheduled agent_args field-misaligned (city:'200', salary=an address, job_role:'Not Available') | data | deferred->open-items#5 (data team; no prompt fix possible)
42 | kkb-kn-out | HIGH | ACTIVE->FLAGGED | apply_job -> 404 'Invalid or missing profile_id' on the Karnataka BAP even with a VALID profileId from a successful create_profile | backend | Flagged - Backend Issue (sheet row 84, open-items#10) - 7e5e1173/ab930586; likely create(UP-interface)/apply(Karnataka-BAP) cross-ecosystem mismatch
43 | kkb-hi-out (+kn twin) | HIGH | ACTIVE->RESOLVED | Earlier 'apply glitch' (skip create/false success/empty profile_id) - root cause was a TEST-DATA artifact (new_seeker='No' + tester DID has no profile = impossible state) | design | RESOLVED - removed ${new_seeker}, restructured to fetch-driven; validated live 7e5e1173/ab930586 (get_profile always first -> create -> apply)
44 | kkb-kn-in | MED | ACTIVE (localization) | Inventory JSON is Karnataka industrial jobs but the descriptor/synonym/sample prose describes UP/NCR retail (Burger King, Ghaziabad/Noida) not in the inventory | sync/data | found via combined-build review; open-items#11 (reconcile live first, then align prose)
45 | combined bots (5) | - | BUILD-FINDING | v0 additive merge preserves outbound byte-for-byte but the shared flow still assumes ${recommendations}/${new_seeker}+permission-ask -> inbound branch misfires | design | RESOLVED via v1 direction-aware pass; 5 experimental agents created (REPORT G.5/G.6)
46 | combined bots (5) | HIGH | BLOCKER | ${call_direction} is NOT injected on POST /api/call (absent from agent_args, also on real standalone outbound) -> combined branch ambiguous -> bot defaults to INBOUND (used hardcoded inventory not ${recommendations}, welcome greeting) on an OUTBOUND trigger | platform | Flagged - open-items#12; needs LitWiz/Raya to confirm when/how call_direction is set; combined approach unvalidated until then - repro b2e9e1e9

## Tests
Bot | Scenario | call_uuid | Result | Notes
kkb-hi-signals 115b38a5 | new-seeker apply | fb1283cb | FAIL -> FIXED | create_profile omitted location -> draft -> apply_job 422 PROFILE_NOT_LIVE. Fix: location made a REQUIRED param on both Signals bots (curl-grounded). Analyser D40.
kkb-hi-signals 115b38a5 | existing-seeker happy path | b83e86de | PASS | Picked the LIVE profile (ignored draft), relevance filter (only Data Entry shown), consent line, apply success, Phase-2 asked area (gender present->skipped), end-confirm incl. gender.
kkb-hi-signals 115b38a5 | not interested (declines at gate) | 4e624597 | PASS | 29 s; polite close, no push, no get_profile, no pitch.
kkb-hi-signals 115b38a5 | wants a different job | a0c24a1d | PASS (feature gap) | Applied to Remote CSE (correct job_id) on the live profile. GAP: never offered to update the stored role -> role-update feature added.
kkb-hi-signals 115b38a5 | role-update offer verify | 15e3f9d9 | PASS | Bot offered 'your role is X - update to Y?', called update_profile(role), then apply success. Minor: set a vague role ('Remote Work').
kkb-kn-signals 33037201 | cooperative existing-seeker | b3ef7abe | PASS | Full parity with Hindi: live-selection, role-confirm, apply success, Phase-2 area (gender skipped), end-confirm, graceful KN close. Minor: 'ಅಪ್ಲೈ ಆಗಿದೆ' x2.
kkb-kn-out 87ab9108 | cooperative + memory-substitution probe | fa530906 | findings | (1) D34 ACTIVE - hold narrated + 'info received' on an EMPTY fetch -> PORT neutral-hold fix (done). (2) D32 LATENT - didn't resume contact_memory journey; get_profile fired. (3) phone +9197946350285 -> 400 (dicey: harness-DID artifact). (4) age read-back worked.
DKB 57814ac8 / d1a1614f | static + historical | cf3fc048 | FIXED (deployed, verify pending) | D5 callback-invite close + D34 narrated silent tools, both confirmed in the historical call; both fixed + deployed Hi+Kn. DKB-Kn live verify pending.
kkb-kn-out 87ab9108 | fetch-driven new-caller (KN) | ab930586 | PARTIAL (flow OK; apply blocked) | get_profile fired FIRST -> empty [] -> new-caller path -> create_profile before apply -> no false success -> age/gender gate. This call: phone mangled +9197946350285 -> create 400. Fetch-driven flow validated; D34 neutral hold confirmed.
kkb-kn-out 87ab9108 | fetch-driven new-caller retest (KN) | 7e5e1173 | PARTIAL (flow OK; apply 404 backend) | Clean phone +917946350285 -> get_profile empty -> create_profile SUCCESS (profileId 5822b168) -> apply_job 404 'Invalid or missing profile_id' on Karnataka BAP (issue #42, backend). new_seeker-removal VALIDATED; apply blocked by backend, not prompt.
kkb-hi-combined 3f521174 | OUTBOUND smoke (call_direction check) | b2e9e1e9 | BLOCKER FOUND | Triggered OUTBOUND with real ${recommendations}, but the bot ran the INBOUND branch: welcome greeting + presented hardcoded-inventory jobs (CY Future/Weavings), NOT the passed recommendations. agent_args has NO call_direction (issue #46). Combined approach unvalidated until platform confirms call_direction injection.

## Fixes
Fix | Bots + agent uuids | Change | Deployed (rollback snapshot) | Verified?
Signals location-required (D40) - new-seeker apply-blocker | kkb-hi-signals 115b38a5, kkb-kn-signals 33037201 | Added location to create_profile.parameters.required (tool-schema PATCH, not prose) -> profile mints live | 2026-07-29 (Raya tool PATCH) | RESOLVED - post-fix applies succeed (b83e86de, b3ef7abe)
Signals live-item selection (D37) | kkb-kn-signals 33037201 (+ Hi twin) | Select profile by lifecycle_status:'live', never items[0]; never apply to a draft while a live item exists | 2026-07-29 (snap ...kkb-kn-signals-2026-07-29_163727) | RESOLVED - b3ef7abe picks live profile, applies
Signals role-update offer + 1:1 profile | kkb-hi-signals 115b38a5, kkb-kn-signals 33037201 | On role-mismatch, offer once to update the stored role -> update_profile(role); treat profile:user as 1:1 (use only the live item) | 2026-07-29 | VERIFIED - feature-gap found a0c24a1d, confirmed 15e3f9d9
KKB inbound D31 - new-caller apply-404 | kkb-hi-in b6222233, kkb-kn-in 4ac90bf1 | create_profile FIRST -> WAIT for its result -> then apply_job with the returned profile_id; forbid same-turn create+apply / empty profile_id | 2026-07-30 (Hi snap ...kkb-hi-in-2026-07-30_003534 sha 9b92a60e; Kn snap ...kkb-kn-in-2026-07-30_004810 sha 9c47ef45, reconciled to live inventory first) | verify-pending: inbound (historical repro 5449910e, 34f1f587)
KKB inbound D34 - neutral hold | kkb-hi-in b6222233, kkb-kn-in 4ac90bf1 | hold_message = neutral 'एक मिनट' / 'ಒಂದು ನಿಮಿಷ' for get_profile/create_profile/update_profile; only apply_job keeps a spoken bridge | 2026-07-30 (Hi snap ...kkb-hi-in-2026-07-30_003943 sha 1b20779a; Kn same reconcile pass ...004810) | verify-pending: inbound
DKB D5 - callback-invite close | dkb-hi-out 57814ac8, dkb-kn-out d1a1614f | Close reframed so future contact is the team reaching out, not 'call me back' (kept 'Goodbye') | 2026-07-30 (Hi snap ...dkb-hi-out-2026-07-30_024108 sha 6edaca1f; Kn snap ...dkb-kn-out-2026-07-30_024109 sha 835f4705) | verify-pending: DKB Kn call (repro cf3fc048)
DKB D34 - empty hold_message | dkb-hi-out 57814ac8, dkb-kn-out d1a1614f | hold_message='' on EVERY tool call (DKB uses no 'one moment' filler) | 2026-07-30 (same snaps as DKB D5, ...024108 / ...024109) | verify-pending: DKB Kn call
KKB outbound D34 - neutral hold | kkb-hi-out da612923, kkb-kn-out 87ab9108 | Neutral hold for get_profile/create_profile/update_profile (ported from the Signals/inbound D34 fix) | 2026-07-30 (Hi snap ...kkb-hi-out-2026-07-30_024527 sha 3d8606c8; Kn snap ...kkb-kn-out-2026-07-30_024528 sha 0c195839) | VERIFIED live - neutral 'ಒಂದು ನಿಮಿಷ' hold in 7e5e1173/ab930586
KKB outbound - remove ${new_seeker} -> fetch-driven | kkb-hi-out da612923, kkb-kn-out 87ab9108 | Replaced the new_seeker branch-router with ALWAYS get_profile-first -> branch on the RESULT (profile->returning, empty->new caller); removed the ${new_seeker} var + all 13 refs; apply two-step (create->WAIT->apply) unchanged | 2026-07-30 commit ebbb3e2 (snap pre-deploy-kkb-hi-out-...040146 / kkb-kn-out-...040147) | Flow VALIDATED live (7e5e1173/ab930586: get_profile always first, create before apply, no false success). Apply itself blocked by backend 404 (issue #42).
kkb-kn-out endpoint PATCH (get_profile/apply_job) | kkb-kn-out 87ab9108 | Briefly re-pointed to UP hosts on a wrong drift-hypothesis; REVERTED on owner correction ('Karnataka doesn't use those endpoints') | 2026-07-30 (snap raya/snapshots/kkb-kn-out.tools.pre-endpoint-fix.json) | REVERTED - net change none; back on Karnataka endpoints, instructions intact (analyser C10 corrected)

## Combined Bots (bonus)
Combined bot | v1 agent uuid (deploy=false) | v1 review | State | BLOCKER + residual gaps
kkb-hi-combined | 3f521174 | outbound OK / inbound FIX_NEEDED | v1 built + agent CREATED | BLOCKER: call_direction NOT injected (open-items#12) - smoke test b2e9e1e9 ran INBOUND (inventory+welcome) on an outbound trigger. Residual: inbound No-Match wording, hr_contact share, sample convos are outbound examples.
kkb-kn-combined | f38da775 | FIX_NEEDED -> structural gaps fixed | v1 built + agent CREATED | BLOCKER: call_direction (#12). Fixed: inbound fetch-gate annotations + Kannada inventory prose rewritten to Karnataka (0 UP leftovers). Residual: inbound spoken nuance.
maya-hi-combined | 904f333f | PASS | v1 built + agent CREATED | BLOCKER: call_direction (#12). ${new_seeker} gated for inbound; Maya divergences preserved. Residual: inbound sample convos + MPL cross-call policy nuance.
dkb-hi-combined | fabda71d | outbound OK / inbound FIX_NEEDED | v1 built + agent CREATED | BLOCKER: call_direction (#12). Residual: Phase-3 job-capture entry is outbound-flavored; create_job companyName + update_job phone are outbound variants.
dkb-kn-combined | 847a85e2 | PASS | v1 built + agent CREATED | BLOCKER: call_direction (#12). Kannada twin; inbound routing folded. Residual: minor outbound-framed shared headers.